## COST ESTIMATE
eCommerce Server Platform V1.0 Cost/Budjet Estimation
|  |  | Resource | Task | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | SUM / h | €/h | TOTAL
Work Category | Price €/h, VAT 0% | VAT 25,5%
Project management | 90 | 20.25 | Burzachechi Sol | Project management | [9 empty] | 0 | 90 | 0
Server maintananc/administration | 65 | 14.625 |  | Server maintananc/administration | [9 empty] | 0 | 65 | 0
Familiarization | 50 | 11.25 |  | Familiarization | 7 | 7 | 6 | 6 | 15 | 15 |  |  |  | 56 | 50 | 2800
Planning/Design | 80 | 18 |  | Planning | S1: 1; S2: 2; S3: 1; S4: 10; S8: 4 | 18 | 80 | 1440
Implementation | 80 | 18 |  | Implementation | 1 | 1 | 1 | 1 | 1 | 7 | 8 |  | 4 | 24 | 80 | 1920
Documentation | 60 | 13.5 |  | Documentation €45/hour | S7: 15; S8: 5 | 20 | 60 | 1200
Testing | 60 | 13.5 |  | Testing | S6: 15; S7: 10 | 25 | 60 | 1500
Meetings | 80 | 18 |  | Meetings | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 14 | 80 | 1120
Other | 70 | 15.75 |  | Other | S8: 2 | 2 | 70 | 140
[5 empty] | S8: Total: | 159
|  |  | Helminen Valtteri | Project management | [9 empty] | 0 | 90 | 0
|  |  |  | Server maintananc/administration | [9 empty] | 0 | 65 | 0
|  |  |  | Familiarization | 7 | 7 | 6 | 6 | 15 | 15 |  |  |  | 56 | 50 | 2800
|  |  |  | Planning | S1: 1; S2: 2; S3: 1; S4: 10; S8: 4 | 18 | 80 | 1440
WORK CATEGORY TOTAL PRICE |  |  |  | Implementation | 1 | 1 | 1 | 1 | 1 | 5 | 10 |  | 4 | 24 | 80 | 1920
|  |  |  | Documentation €45/hour | S1: 1; S2: 1; S7: 10; S8: 5 | 17 | 60 | 1020
Project management | 3870 |  |  | Testing | S6: 10; S7: 10 | 20 | 60 | 1200
Server administration | 3510 |  |  | Meetings | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 14 | 80 | 1120
Familiarization | 14200 |  |  | Other | S8: 2 | 2 | 70 | 140
Planning | 8880 |  |  |  | S8: Total: | 151
Implementation | 14640 |  | Hyvärinen Sami | Project management | S0: 1; S1: 2; S2: 2; S3: 1 | 6 | 90 | 540
Documentation | 4920 |  |  | Server maintananc/administration | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 36 | 65 | 2340
Testing | 2700 |  |  | Familiarization | S0: 7; S1: 7; S2: 6; S3: 6; S4: 12 | 38 | 50 | 1900
Meetings | 6720 |  |  | Planning |  | 1 | 2 | 1 | 10 | 4 |  |  | 4 | 22 | 80 | 1760
Other | 840 |  |  | Implementation | 1 | 1 | 1 | 1 | 1 | 10 | 10 |  | 4 | 29 | 80 | 2320
|  |  |  | Documentation €45/hour | S7: 6; S8: 5 | 11 | 60 | 660
|  |  |  | Testing | [9 empty] | 0 | 60 | 0
|  |  |  | Meetings | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 14 | 80 | 1120
|  |  |  | Other | S8: 2 | 2 | 70 | 140
[5 empty] | S8: Total: | 158
|  |  | Iiskola Lassi | Project management | 5 | 5 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 34 | 90 | 3060
|  |  |  | Server maintananc/administration | [9 empty] | 0 | 65 | 0
|  |  |  | Familiarization | 7 | 7 | 6 | 6 | 10 | 10 |  |  |  | 46 | 50 | 2300
|  |  |  | Planning | S1: 1; S2: 2; S3: 1; S4: 10; S8: 4 | 18 | 80 | 1440
|  |  |  | Implementation | 1 | 1 | 1 | 1 | 1 | 10 | 12 | 6 | 4 | 37 | 80 | 2960
|  |  |  | Documentation €45/hour | S2: 1; S3: 1; S7: 6; S8: 5 | 13 | 60 | 780
|  |  |  | Testing | [9 empty] | 0 | 60 | 0
|  |  |  | Meetings | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 14 | 80 | 1120
|  |  |  | Other | S8: 2 | 2 | 70 | 140
[5 empty] | S8: Total: | 164
|  |  | Jayani Kothalawala | Project management | [9 empty] | 0 | 90 | 0
|  |  |  | Server maintananc/administration | [9 empty] | 0 | 65 | 0
|  |  |  | Familiarization | 7 | 7 | 6 | 6 | 16 | 6 |  |  |  | 48 | 50 | 2400
|  |  |  | Planning |  | 1 | 2 | 1 | 4 | 7 |  |  | 4 | 19 | 80 | 1520
|  |  |  | Implementation | 1 | 1 | 1 | 1 | 1 | 7 | 15 | 7 | 4 | 38 | 80 | 3040
|  |  |  | Documentation €45/hour | S7: 5; S8: 5 | 10 | 60 | 600
|  |  |  | Testing | [9 empty] | 0 | 60 | 0
|  |  |  | Meetings | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 14 | 80 | 1120
|  |  |  | Other | S8: 2 | 2 | 70 | 140
[5 empty] | S8: Total: | 131
|  |  | Suutarinen Eetu | Project management | [9 empty] | 3 | 90 | 270 | bar: S1 to S3
|  |  |  | Server maintananc/administration | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 18 | 65 | 1170
|  |  |  | Familiarization | 7 | 7 | 6 | 6 | 12 | 2 |  |  |  | 40 | 50 | 2000
|  |  |  | Planning |  | 1 | 2 | 1 | 3 | 5 |  |  | 4 | 16 | 80 | 1280
|  |  |  | Implementation | 1 | 1 | 1 | 1 | 1 | 6 | 12 | 4 | 4 | 31 | 80 | 2480
|  |  |  | Documentation €45/hour | S7: 6; S8: 5 | 11 | 60 | 660
|  |  |  | Testing | [9 empty] | 0 | 60 | 0
|  |  |  | Meetings | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 14 | 80 | 1120
|  |  |  | Other | S8: 2 | 2 | 70 | 140
[5 empty] | S8: Total: | 135
|  |  |  | Software Licenses & Tools | [9 empty] | 9 | 0 | 0 | bar: S0 to S8
|  |  |  | Hardware & Equipment | [9 empty] | 9 | 0 | 0 | bar: S0 to S8
|  |  |  | Cloud Services / Hosting | [9 empty] | 9 | 40 | 360 | bar: S0 to S8
|  |  |  | Third-Party Integrations / APIs | [9 empty] | 9 | 60 | 540 | bar: S0 to S8
|  |  |  | External Services / Contractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Training & Onboarding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 25 | 125
|  |  |  | Travel & Communication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Administrative & Overhead Costs | [9 empty] | 9 | 80 | 720 | bar: S0 to S8
|  |  |  | Contingencies / Buffers 2% of total | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2343 | 2343
[5 empty] | S8: Total |  |  | 4088
[5 empty] | S8: Total Working Hours |  |  | 898
[5 empty] | S8: TOTAL WORK COST |  |  | 60280
[5 empty] | S8: Other Costs |  |  | 4088
[5 empty] | S8: Profit 35 % |  |  | 22528.8
[5 empty] | S8: TOTAL |  |  | 86896.8
[5 empty] | S8: VAT 25,5% |  |  | 22158.684
[5 empty] | S8: TOTAL incl. VAT |  |  | 109055.484

## FEATURE PRICES
FEATURE PRICING
Description | In Plan | Priority |  | Familiarization | Design | Implementation | Testing | Documentation | Deployment | Total Hours | Total Work Price | With 35 % Profit | With VAT
|  |  | Hour Price | 50 | 80 | 80 | 60 | 60 | 65
|  |  | Total Price | 4650 | 3440 | 8960 | 1800 | 2220 | 1950 | 345 | 23365 | 31542.75 | 39586.1513
FE002 Secure service access | YES | P1 |  | 2 | 1 | 1 | 2 | 2 | 2 | 10 | 630 | 850.5 | 1067.3775
FE003 Dockerized Service Production | YES | P1 |  | 10 | 3 | 9 | 8 | 4 | 8 | 42 | 2700 | 3645 | 4574.475
FE010 Integrate with a vulnerability scanning tool to automatically detect and report known vulnerabilities | YES | P3 |  | 14 | 8 | 22 | 5 | 6 | 8 | 63 | 4280 | 5778 | 7251.39
FE023 Integrate with version control systems (e.g., Git) | YES | P3 |  | 25 | 10 | 25 | 5 | 10 | 2 | 77 | 5080 | 6858 | 8606.79
FE081 Ensure efficient bug reporting and triage processes | YES | P3 |  | 22 | 11 | 22 | 5 | 5 | 8 | 73 | 4860 | 6561 | 8234.055
FE192 Integration with Popular Gateways: Integrate with a wider range of popular payment gateways (e.g., Stripe, PayPal, Square, Amazon Pay, Apple pay, Google pay) | YES | P1 |  | 20 | 10 | 33 | 5 | 10 | 2 | 80 | 5470 | 7384.5 | 9267.5475
[9 empty] | TOTAL | 345 | 23020 | 31077 | 39001.635